## General
Triton Robotics 2021-2022 Gannt Chart
Month | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | Legend
| 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | Planned
Specifics | [11 empty] | WIP
RMUC Timeline (Online) | Competition Registration | Rules Exam and Season Schedule |  | Referee System Exam | Midterm Assessment |  |  |  | Final Assessment and Competition Feedback |  | Practice Competition | Completed
RMUC Timeline (Offline) | [9 empty] | International Teams Regional Competition | Final Tournament | Canceled
Robot Development | Recruitment and Training | Brain Storm the Design | First Generation Design Complete | First Generation Design Prototype | First Generation Design Testing and Midterm Assessment | Second Generatio Design and Development | Further Testings and Development | Arena Components Prototype | Referee System installation and Operator Training | Practice Competition
Promotion | Recruitment and Training | Media Weekly Post | Branding Design | RMUL operation team recruit | Media Weekly Post | [5 empty] | Triton Robotics Year Book
Business | Recruitment and Training | Finish Business Packet and Sponsorship Letter | Reaching Out to Potential Sponsors | [7 empty] | Competition Updates to Sponsors

## Aerial
Aerial Gannt Chart 2021-2022
Month | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
Focus of the Month | Recruit Training | Recruit Training | CAD Finalization | Part Ordering/ Construction | Prototype Fabrication | Analysis and Redesign | Final Material Order | Drone Fabrication | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Propulsion system | Analysis and Research of Propulsion Systems | Further Research and Simulations of Propulsion Systems | Determine Parts for Ordering | Order Parts and Begin Assembly | Assemble and Test Flight Behavior | Performance Analysis and order different parts if necessary |  |  |  |  | Completed
Airframe |  | Research and CAD of Aerial Drame | Finalize CAD and order Parts | Prototype Airframe Construction | Finish Construction and Start Testing | Performance Analysis & Redesign | Verify Final Design and Order Additional Parts | Final Aerial Fabrication for Competition |  |  | Canceled
Turret | Analysis of 2020-2021 Sentry Turret | Begin CAD modifications to Sentry Turret | CAD of Aerial Turret and Integration with Frame | Prototype Turret Construction | Finish Construction and Start Testing | Performance Analysis & Redesign | Verify Final Design and Order Additional Parts | Final Aerial Fabrication for Competition
Battery and electrical system |  | Evaluate power system and calculate the expected fligth time | Create a schematic of the wiring | Order the batteries |  | Test Battery Performance Through Flight Data
Fabrication |  |  | Finalize Prototype Bill of Materials | Material and Part orders for Prototyping | Fabrication of Prototype |  | Final Parts order | Final Aerial Fabrication for Competition
CV |  |  |  |  | Program on computer vision on prototype turret |  |  | Test motion planning and shooting of final Aerial |  | Verification that Electronics are Operational
Embedded |  |  |  | Work on motion planning with lidar on prototype drone | Program protype turret | Program the turret to auto-aim using computer vision |  |  | Drone operator training

## Hero
Hero Gannt Chart 2021-2022
Month | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
Focus of the Month | Recruit Training | Recruit Training | CAD Finalization | Part Ordering | Prototype Fabrication | Analysis and Redesign | Final Material Order | Hero Fabrication | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Suspension | Brainstorming and Research of Suspension Designs | CAD of Various Designs and Design Matrix | Finalized CAD of Prototype Suspension | Order Parts & Prepare Fabrication Instructions | Prototype Suspension Construction & Mount to Chassis | Performance Analysis & Redesign | Order Parts & Prepare Fabrication Instructions | Final Suspension Construction & Mount to Chassis | Maintenance Training | Blank for any Emergency Needs | Completed
Chassis |  | Analysis and redesign of 2020-2021 Hero Chassis | CAD of New Design & Test compatability with Suspension | Verify Prototype Chassis Design & prepare Fabrication instruction | Prototype Chassis Construction | Performance Analysis & Redesign | Verify Prototype Chassis Design & prepare Fabrication instruction | Final Chassis Construction | Driver Training | Blank for any Emergency Needs | Canceled
Turret |  |  | Assembly Check of Current Design & Test Slip-ring Compatibility | Order Replacement and Redesigned Parts | Replace Damaged or Redesigned Parts & Mount to Chassis | Performance Analysis & Redesign | Order Replacement and Redesigned Parts | Replace Damaged or Redesigned Parts & Mount to Chassis | Driver Training | Blank for any Emergency Needs
Battery and electrical system |  |  |  | Quality Verification of Current Hero Electronics | Placing Electronics on Hero and Testing | Verify Ease of Access and Maintenance | Ordering New Electronics if Necessary | Placing Electronics on Hero and Verifying if Hero is Operational | Maintenance Training | Blank for any Emergency Needs
Fabrication |  |  | Finalize Prototype Bill of Materials | Material and Part orders for Prototyping | Fabrication of Prototype | Verify Ease of Access and Maintenance | Final Material and Part Orders | Final Hero Fabrication for Competition | Maintenance Training | Blank for any Emergency Needs
CV | [5 empty] | Testing CV Code Compatibility with Prototype |  |  | Testing CV Code Compatibility with Hero | Blank for any Emergency Needs
Embedded |  |  |  | Reorganize Electronic Layout & Test Compatibility with Protoype | Testing and Troubleshooting of Program and Electronics | Verify Electronics Layout and Reorganize if Necessary |  | Verification that Electronics are Operational | Mounting Electronics to Hero for Competition | Blank for any Emergency Needs

## Infantry
Infantry Gannt Chart 2021-2022
Week | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
Focus of the Month | First Prototype | First Prototype | Second Prototype (CAD) | Second Prototype Fabrication | Analysis and Redesign | Final Design Fabrication | Final Material Order | Driver Training | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Suspension | Small Modifications on The Suspension Designed During Summer | Assembly | Change The Arm Length and Design a 3D-Printed Cover | 3D-Print the Covers and Order Screws | Redesign Based on Performance | Fabricate Parts Necessary for Final Design (May Need to Change Springs) |  | Driver Training | Maintenance Training | Blank for any Emergency Needs | Completed
Chassis | Brainstorm on How to Mount Electronics on The Chassis | Spray Paint and Assembly | Move Square Tubing Below Chassis Base Plate & Make Room for Electronics and Protector | Fabricate New Chassis Design | Redesign Based on Performance | Fabricate Parts Necessary for Final Design |  | Driver Training | Blank for any Emergency Needs | Blank for any Emergency Needs | Canceled
Turret | Design a Test Turret Plate for flywheels | Test out Best Flywheel Distance | Modify the Four-Bar Linkage to Reduce Friction | Test out Best Flywheel Distance | Redesign Based on Performance | Fabricate Parts Necessary for Final Design |  | Driver Training | Blank for any Emergency Needs | Blank for any Emergency Needs
Battery and electrical system | Collect All Necessary Electrical Components | Solder Wires and Plan out the Best Wiring for Infantry |  | Solder Wires and Incoperate Slip Ring | Verify Ease of Access and Maintenance |  | Ordering New Electronics if Necessary | Driver Training | Blank for any Emergency Needs | Blank for any Emergency Needs
Fabrication | Laser Cut Parts and Assemble Prototype | Laser Cut Parts and Assemble Prototype |  | Consult with the Machine Shop Staff on CNCing Carbon Fiber and Assemble Prototype |  | Fabricate Parts Necessary for Final Design and Assembly | Order Extra Parts in Case of Emergency |  | Blank for any Emergency Needs | Blank for any Emergency Needs
CV |  |  |  |  | Testing CV Code Compatibility with Prototype |  | Testing CV Code Compatibility with Infantry |  | Maintenance Training | Blank for any Emergency Needs
Embedded | Testing and Troubleshooting of Program and Electronics | Reorganize Electronic Layout & Test Compatibility with Protoype |  |  | Reorganize Electronic Layout & Test Compatibility with Protoype | Verify Electronics Layout and Reorganize if Necessary |  | Verification that Electronics are Operational | Mounting Electronics to Infantry for Competition | Blank for any Emergency Needs

## Sentry
Sentry Gantt Chart 2021-2022
Month | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
Focus of the Month | Recruit Training | Recruit Training | CAD Finalization | Part Ordering | Prototype Fabrication | Analysis and Redesign | Final Material Order | Sentry Fabrication | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Chassis |  | Analysis and redesign of 2020-2021 Sentry Chassis | CAD of New Design & Test compatability with Turret | Approve Prototype Chassis Design & prepare Fabrication | Prototype Chassis Construction | Performance Analysis & Redesign | Verify Prototype Chassis Design & prepare Fabrication instruction | Final Chassis Construction | Driver Training | Blank for any Emergency Needs | Completed
Turret |  | Analysis and redesign of 2020-2021 Sentry Turret | CAD of New Design & Test compatability with Chassis | Approve Prototype Turret Design & prepare Fabrication | Prototype Turret Construction | Performance Analysis & Redesign | Verify Prototype Chassis Design & prepare Fabrication instruction | Final Chassis Construction | Driver Training | Blank for any Emergency Needs | Canceled
Fabrication |  |  | Finalize Prototype Bill of Materials | Material and Part orders for Prototyping | Fabrication of Prototype | Verify Ease of Access and Maintenance | Final Material and Part Orders | Final Sentry Fabrication for Competition | Maintenance Training | Blank for any Emergency Needs
CV | [5 empty] | Testing CV Code Compatibility with Prototype |  |  | Testing CV Code Compatibility with Sentry | Blank for any Emergency Needs
Embedded |  | Familiarize Recruits with Sentry electronics and mechanisms | Assess Electronic Layout for Slip ring and Test code on 2020-2021 Sentry | Test code on 2020-2021 Sentry and verify Electronic Layout | Testing and Troubleshooting of Program and Electronics | Verify Electronics Layout and Reorganize if Necessary |  | Verification that Electronics are Operational | Mounting Electronics to Sentry for Competition | Blank for any Emergency Needs

## Engineer
Engineer Gannt Chart 2021-2022
Month | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
| Recruit Training | Recruit Training | CAD Finalization | Part Ordering | Prototype Fabrication | Analysis and Redesign | Final Material Order | Sentry Fabrication | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Pneumatics |  | Research on Pneumatics and Related Wiring | Pneumatics Computation and BOM | Purchase and Manufacturing Components for Testing | Assemble and Testing | Procedure and Performance Documentation |  |  |  | Blank for any Emergency Needs | Completed
Mineral Acquisition |  | Brainstorm the Design with the subteam | Finalize CAD design and provide BOM | Purchase and Manufacturing Components for Testing | Be able to catch dropping minerals | Performance Analysis and Redesign | Purchase new components if needed | Be able to catch mineral on the Ground | Driver training | Blank for any Emergency Needs | Canceled
Storage |  | Brainstorm the Design with the subteam | Finalize CAD design and provide BOM | Purchase and Manufacturing Components for Testing | Be able to store and rotate at least one mineral | Performance Analysis and Redesign | Purchase new components if needed | Be able to store and rotate two minerals | Driver training | Blank for any Emergency Needs
Chassis | Wiring Diagram | CAD Design Improvement | Finalize CAD design and provide BOM | Purchase and Manufacturing Components for Testing | Bumpy Road Testing | Performance Analysis and Redesign | Violent Test | Update Performance Analysis |  | Blank for any Emergency Needs
Rescue Mechanism | Brainstorm the Design with the subteam | Initial CAD Design and Cooperation with Other Sub-teams | Finalize CAD design and provide BOM | Purchase and Manufacturing Components for Testing | Matching Test | Performance Analysis | Aiming for rescuing two robots at the same time | Matching Test | Driver training | Blank for any Emergency Needs
CV |  |  | Barcode Recognition | Apply barcode recognition and test rotation |  |  | Algorithms Detecting Flashing Light on Resource Island | Test cv code and adjust claw reaction time |  | Blank for any Emergency Needs
Embedded |  |  |  | Pneumatic Testings | Complete the Testings for First Generation Design and Coding | Testing and Troubleshooting of Program and Electronics | Verification that Electronics are Operational | Installing the Referee System for Driver Training | Driver training | Blank for any Emergency Needs

## Dart
Dart Gantt Chart 2021-2022
Week | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | Legend
Focus of the Month | Recruit Training | Recruit Training | CAD Finalization | Part Ordering | Prototype Fabrication | Analysis and Redesign | Final Material Order | Final Fabrication | Competition Preparations | Competition | Planned
Specifics | [10 empty] | WIP
Dart Launcher | Intial Ideas and Design | Intial Ideas and Design | Narrow Design and Finish Initial Cad of the Launcher | Order Referee System, Flywheels, and Other Custom Parts | Have Complete Prototype Built | Test Prototype and Continue Iterating | Order Any New Parts for Redesigns. Have Final CAD. | Have a Final Complete Dart Launcher | Operator Training and Organize for Travel. | Blank for any Emergency Needs | Completed
Dart | Intial Ideas and Design | Intial Ideas and Design | Continue Design Process and Begin CADing Dart | Finish CAD of Dart and Order Materials | Have One Complete Dart Built | Test Prototype and Continue Iterating. Build the rest of Darts | Order Any New Parts for Redesigns. Have Final CAD. | Have Four Completely Built Darts (possibly spares). | Organize for Travel. | Blank for any Emergency Needs | Canceled
Fabrication |  |  |  | Collect All Parts for Prototype Fabrication | Build and Assemble One Launcher and One Dart | Continue Adding Improvements to Initial Prototype | Collect Parts For Final Fabrication | Build and Assemble Final Launcher and 4 Darts | Get Extra Parts and Build Spare Darts. Organize For Travel. | Blank for any Emergency Needs
CV |  | Research | Research | Order any Hardware for Prototyping | Build Prototype Self-Guided Dart | Research and Redesign Iteratively | Order Necessary Hardware | If research and Development Goes Well Build 4 Darts with CV | Continue Testing and Developing Software | Blank for any Emergency Needs
Embedded |  |  | Order Necessary Hardware | Order Necessary Hardware | Put Electronics on the Prototype | Redesign Electronic Placement and Work on Controls for Launcher | Order Anymore Hardware | Finalize Electronincs Configuration for Launcher and Dart | Finailize Controls for Launcher and Dart | Blank for any Emergency Needs